## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Navbar | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Authentication | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Homepage | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Filter products | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Add to cart | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Carousel | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Render products to shop | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Checkout | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
History and history detail | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Receive orders(admin) | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Logic with product in cart | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trung Hiếu |  | 2023-02-10 | 100% | Nguyễn Trần Hoàng Duy
Responsive | 20/9/2023 | 2023-01-10 | 100% | All |  | 2023-02-10 | 100% | All
Adminpage | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
CRUD product(admin) | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu
Search and filter product(admin) | 20/9/2023 | 2023-01-10 | 100% | Nguyễn Trần Hoàng Duy |  | 2023-02-10 | 100% | Nguyễn Trung Hiếu